## Tracker
Project: QA Material Review
Rating system: Mostadam commercial D+C (2019)
Sustainability Material Tracker · generated 2026-10-27 · credit columns as at 2026-10
[12 empty] | Product |  |  | Quantities | [5 empty] | Counts toward (latest revision) | [6 empty] | SMQ answers by credit |  |  |  | Review
S/N | Material Submittal Reference | Rev | Approval Status | Description | Date of Submission | Sustainability Applicable | Discipline | Supplier Name | Material Delivery date | Material Delivery (PO Number) | Manufacturer Name | Country of Origin | Location of use | Interior | BOQ weight (t) | BOQ volume (m³) | BOQ cost (SAR) | Delivered weight (t) | Delivered volume (m³) | Delivered cost (SAR) | MW-05 Recycled steel | MW-05 Recycled aggregates | MW-05 Certified timber | HC-11 Low-VOC adhesives, sealants, paints and coatings | HC-11 Formaldehyde: composite wood and ceilings | RC-01 Materials made in KSA | MW-04 Non-polluting insulation | HC-11 answers | MW-05 answers | RC-01 answers | TC-04 answers | Reviewed on | Reviewed by | Consultant remarks
1 | QA-MTS-001 | Rev 00 | C - Revise and resubmit | Interior paints and coatings: QA Paint A | 2026-09-10 | Applicable | Architecture | QA Supplier Co | see Rev 02 |  | QA Paints LLC | Saudi Arabia | Interior walls | Yes | 1200.5 |  | 50000 |  |  |  | replaced | replaced | replaced | replaced | replaced | replaced | replaced | Yes 35 g/L; Yes |  | Yes; Yes |  | 2026-09-20 | QA Reviewer | QA: VOC report expired, resubmit
2 | QA-MTS-001 | Rev 01 | A - Approved | Interior paints and coatings: QA Paint A | 2026-09-10 |  | Architecture | QA Supplier Co | see Rev 02 |  | QA Paints LLC | Saudi Arabia | Interior walls | Yes | 1200.5 |  | 50000 |  |  |  | replaced | replaced | replaced | replaced | replaced | replaced | replaced | Yes 35 g/L; Yes |  | Yes; Yes |  | 2026-10-10
3 | QA-MTS-002 | Rev 00 | A - Approved | Reinforcement steel: QA Rebar A | 2026-09-01 |  |  |  | 2026-09-28 2026-10-20 |  |  |  |  | Yes | 1000 |  | 400000 | 500 |  | 120000 | Counts |  |  |  |  | Counts |  |  | Yes; Yes | Yes; Yes |  | 2026-10-05
4 | QA-MTS-002 | Rev 00 | Under review | Reinforcement steel: QA Rebar B | 2026-09-01 | [8 empty] | Yes | 500 | [5 empty] | Pending |  |  |  |  | Pending |  |  | Yes; Yes | Yes; Yes
5 | QA-MTS-002 | Rev 00 | C - Revise and resubmit | Reinforcement steel: QA Rebar C | 2026-09-01 | [8 empty] | Yes | 250 | [5 empty] | Pending |  |  |  |  | Pending |  |  | Yes; Yes | Yes; Yes |  | 2026-09-05
6 | QA-MTS-002 | Rev 00 | D - Rejected | Reinforcement steel: QA Rebar D | 2026-09-01 | [8 empty] | Yes | 100 | [13 empty] | Yes; Yes | Yes; Yes |  | 2026-10-01
7 | QA-MTS-001 | Rev 00 | A - Approved | Interior paints and coatings: QA Exterior paint | 2026-09-10 |  | Architecture | QA Supplier Co | [5 empty] | No | 10 | [10 empty] | Counts |  | Yes; Yes |  | Yes; Yes |  | 2026-10-12
8 | QA-MTS-002 | Rev 00 | Under review | Reinforcement steel: QA Bike rack | 2026-09-01 | [8 empty] | Yes | [11 empty] | Pending |  |  |  | N/A; N/A | N/A; N/A
9 | QA-MTS-001 | Rev 02 | Under review | Interior paints and coatings: QA Paint A | 2026-09-10 |  | Architecture | QA Supplier Co | 2026-09-25 2026-10-15 | PO-QA-1 | QA Paints LLC | Saudi Arabia | Interior walls | Yes | 1200.5 |  | 50000 | 500 |  | 5000 | [7 empty] | Yes 35 g/L; Yes |  | Yes; Yes

## Answers
Submittal | Product | Rev | Status | Section | Mostadam credit | LEED reference | Required documents / parameters | Answer | Value | Unit | Project target | Remark | Documents (issue date)
QA-MTS-001 | QA Paint A | Rev 00 | C | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 1) Environmental Product Declaration (EPD): Provide any of the below: a) Manufacturer declared life-cycle assessment with at least a cradle to gate scope. b) Manufacturer reviewed product specific Type III EPD with at least a cradle to gate scope c) Third party verified industry-wide Type III EPD with at least a cradle to gate scope. | Yes
QA-MTS-001 | QA Paint A | Rev 00 | C | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 2) Embodied Carbon/LCA Optimization: Provide manufactures prepared Embodied Carbon/LCA Action Plan demonstrating reduction in embodied carbon with at least reduction in GWP. | Yes
QA-MTS-001 | QA Paint A | Rev 00 | C | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) A manufacturer declaration/third party certificate stating the % of post-consumer and % of pre-consumer recycled content. Note: Waste reuse from the same production line should be excluded. 2) If applicable, a manufacturer letter stating the products sourced (extracted, manufactured and purchased) is within 160 km of the project site. | Yes
QA-MTS-001 | QA Paint A | Rev 00 | C | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 3) Invoices/Purchase orders | Yes
QA-MTS-001 | QA Paint A | Rev 00 | C | For all materials | RC-01 |  | 1) Proof of manufacture in KSA, with at least one of the following conditions: - Extracted in KSA - Manufactured in KSA - Final point of assembly in KSA | Yes
QA-MTS-001 | QA Paint A | Rev 00 | C | For all materials | RC-01 |  | 2) Invoices/Purchase orders | Yes
QA-MTS-001 | QA Paint A | Rev 00 | C | For all materials |  | MRc4: Building Product Disclosure and Optimization - Material Ingredients | Provide any of below documentation: - Cradle to Cradle (C2C): Material Health Certificate or is Cradle to Cradle Certified™ Bronze level or higher. - Declare: Designated as Red List Free, LBC Red List Free, or Declared, LBC Red List Approved or LBC Compliant - Global Green Tag or Health Product Declaration (HPDs). Material Ingredient Optimization: Provide anyone of below: - Manufacturer prepared REACH report or PHD Report verified by Global Green TAG - Manufacturer prepared material ingredient screening and Optimization Action Plan - Third party verified Advanced Inventory & Assessment - Third party verified Material Ingredient Optimization | Yes
QA-MTS-001 | QA Paint A | Rev 00 | C | Paints, Coatings (QA) | HC-11 | IEQc2: Low-Emitting Materials | 1) Data sheet or Test Report for Product VOC Content (g/l) complying with the VOC content requirements for wet-applied products AND 2) General emission certificate as per CDPH Standard Method v1,1 or v1.2 2017 with testing lab accreditation under ISO/IEC 17025. | Yes | 35 | g/L | ≤ 50 g/L (QA) | QA remark | Jotun-VOC-content-test-2022.pdf (2023-05-01) RISE-CDPH-emission-report-O100152.pdf (2026-08-01)
QA-MTS-001 | QA Paint A | Rev 00 | C | Paints, Coatings (QA) | HC-11 |  | QA extra row: provide the colour card | Yes
QA-MTS-001 | QA Paint A | Rev 00 | C | QA Waterproofing membranes |  |  | QA membrane datasheet | Yes
QA-MTS-001 | QA Paint A | Rev 01 | A | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 1) Environmental Product Declaration (EPD): Provide any of the below: a) Manufacturer declared life-cycle assessment with at least a cradle to gate scope. b) Manufacturer reviewed product specific Type III EPD with at least a cradle to gate scope c) Third party verified industry-wide Type III EPD with at least a cradle to gate scope. | Yes
QA-MTS-001 | QA Paint A | Rev 01 | A | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 2) Embodied Carbon/LCA Optimization: Provide manufactures prepared Embodied Carbon/LCA Action Plan demonstrating reduction in embodied carbon with at least reduction in GWP. | Yes
QA-MTS-001 | QA Paint A | Rev 01 | A | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) A manufacturer declaration/third party certificate stating the % of post-consumer and % of pre-consumer recycled content. Note: Waste reuse from the same production line should be excluded. 2) If applicable, a manufacturer letter stating the products sourced (extracted, manufactured and purchased) is within 160 km of the project site. | Yes
QA-MTS-001 | QA Paint A | Rev 01 | A | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 3) Invoices/Purchase orders | Yes
QA-MTS-001 | QA Paint A | Rev 01 | A | For all materials | RC-01 |  | 1) Proof of manufacture in KSA, with at least one of the following conditions: - Extracted in KSA - Manufactured in KSA - Final point of assembly in KSA | Yes
QA-MTS-001 | QA Paint A | Rev 01 | A | For all materials | RC-01 |  | 2) Invoices/Purchase orders | Yes
QA-MTS-001 | QA Paint A | Rev 01 | A | For all materials |  | MRc4: Building Product Disclosure and Optimization - Material Ingredients | Provide any of below documentation: - Cradle to Cradle (C2C): Material Health Certificate or is Cradle to Cradle Certified™ Bronze level or higher. - Declare: Designated as Red List Free, LBC Red List Free, or Declared, LBC Red List Approved or LBC Compliant - Global Green Tag or Health Product Declaration (HPDs). Material Ingredient Optimization: Provide anyone of below: - Manufacturer prepared REACH report or PHD Report verified by Global Green TAG - Manufacturer prepared material ingredient screening and Optimization Action Plan - Third party verified Advanced Inventory & Assessment - Third party verified Material Ingredient Optimization | Yes
QA-MTS-001 | QA Paint A | Rev 01 | A | Paints, Coatings (QA) | HC-11 | IEQc2: Low-Emitting Materials | 1) Data sheet or Test Report for Product VOC Content (g/l) complying with the VOC content requirements for wet-applied products AND 2) General emission certificate as per CDPH Standard Method v1,1 or v1.2 2017 with testing lab accreditation under ISO/IEC 17025. | Yes | 35 | g/L | ≤ 50 g/L (QA) | QA remark | Jotun-VOC-content-test-2022.pdf (2023-05-01) RISE-CDPH-emission-report-O100152.pdf (2026-08-01)
QA-MTS-001 | QA Paint A | Rev 01 | A | Paints, Coatings (QA) | HC-11 |  | QA extra row: provide the colour card | Yes
QA-MTS-001 | QA Paint A | Rev 01 | A | QA Waterproofing membranes |  |  | QA membrane datasheet | Yes
QA-MTS-002 | QA Rebar A | Rev 00 | A | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 1) Environmental Product Declaration (EPD): Provide any of the below: a) Manufacturer declared life-cycle assessment with at least a cradle to gate scope. b) Manufacturer reviewed product specific Type III EPD with at least a cradle to gate scope c) Third party verified industry-wide Type III EPD with at least a cradle to gate scope. | Yes
QA-MTS-002 | QA Rebar A | Rev 00 | A | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 2) Embodied Carbon/LCA Optimization: Provide manufactures prepared Embodied Carbon/LCA Action Plan demonstrating reduction in embodied carbon with at least reduction in GWP. | Yes
QA-MTS-002 | QA Rebar A | Rev 00 | A | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) A manufacturer declaration/third party certificate stating the % of post-consumer and % of pre-consumer recycled content. Note: Waste reuse from the same production line should be excluded. 2) If applicable, a manufacturer letter stating the products sourced (extracted, manufactured and purchased) is within 160 km of the project site. | Yes
QA-MTS-002 | QA Rebar A | Rev 00 | A | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 3) Invoices/Purchase orders | Yes
QA-MTS-002 | QA Rebar A | Rev 00 | A | For all materials | RC-01 |  | 1) Proof of manufacture in KSA, with at least one of the following conditions: - Extracted in KSA - Manufactured in KSA - Final point of assembly in KSA | Yes
QA-MTS-002 | QA Rebar A | Rev 00 | A | For all materials | RC-01 |  | 2) Invoices/Purchase orders | Yes
QA-MTS-002 | QA Rebar A | Rev 00 | A | For all materials |  | MRc4: Building Product Disclosure and Optimization - Material Ingredients | Provide any of below documentation: - Cradle to Cradle (C2C): Material Health Certificate or is Cradle to Cradle Certified™ Bronze level or higher. - Declare: Designated as Red List Free, LBC Red List Free, or Declared, LBC Red List Approved or LBC Compliant - Global Green Tag or Health Product Declaration (HPDs). Material Ingredient Optimization: Provide anyone of below: - Manufacturer prepared REACH report or PHD Report verified by Global Green TAG - Manufacturer prepared material ingredient screening and Optimization Action Plan - Third party verified Advanced Inventory & Assessment - Third party verified Material Ingredient Optimization | Yes
QA-MTS-002 | QA Rebar A | Rev 00 | A | All metals | MW-05 | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) Material technical datasheets confirming the recycled content of steel. | Yes |  | % |  |  | RISE-CDPH-emission-report-O100152.pdf (2026-06-01)
QA-MTS-002 | QA Rebar A | Rev 00 | A | All metals | MW-05 | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 2) Purchase orders for all reinforcing or stressing steel installed in the project. | Yes
QA-MTS-002 | QA Rebar B | Rev 00 | Under review | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 1) Environmental Product Declaration (EPD): Provide any of the below: a) Manufacturer declared life-cycle assessment with at least a cradle to gate scope. b) Manufacturer reviewed product specific Type III EPD with at least a cradle to gate scope c) Third party verified industry-wide Type III EPD with at least a cradle to gate scope. | Yes
QA-MTS-002 | QA Rebar B | Rev 00 | Under review | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 2) Embodied Carbon/LCA Optimization: Provide manufactures prepared Embodied Carbon/LCA Action Plan demonstrating reduction in embodied carbon with at least reduction in GWP. | Yes
QA-MTS-002 | QA Rebar B | Rev 00 | Under review | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) A manufacturer declaration/third party certificate stating the % of post-consumer and % of pre-consumer recycled content. Note: Waste reuse from the same production line should be excluded. 2) If applicable, a manufacturer letter stating the products sourced (extracted, manufactured and purchased) is within 160 km of the project site. | Yes
QA-MTS-002 | QA Rebar B | Rev 00 | Under review | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 3) Invoices/Purchase orders | Yes
QA-MTS-002 | QA Rebar B | Rev 00 | Under review | For all materials | RC-01 |  | 1) Proof of manufacture in KSA, with at least one of the following conditions: - Extracted in KSA - Manufactured in KSA - Final point of assembly in KSA | Yes
QA-MTS-002 | QA Rebar B | Rev 00 | Under review | For all materials | RC-01 |  | 2) Invoices/Purchase orders | Yes
QA-MTS-002 | QA Rebar B | Rev 00 | Under review | For all materials |  | MRc4: Building Product Disclosure and Optimization - Material Ingredients | Provide any of below documentation: - Cradle to Cradle (C2C): Material Health Certificate or is Cradle to Cradle Certified™ Bronze level or higher. - Declare: Designated as Red List Free, LBC Red List Free, or Declared, LBC Red List Approved or LBC Compliant - Global Green Tag or Health Product Declaration (HPDs). Material Ingredient Optimization: Provide anyone of below: - Manufacturer prepared REACH report or PHD Report verified by Global Green TAG - Manufacturer prepared material ingredient screening and Optimization Action Plan - Third party verified Advanced Inventory & Assessment - Third party verified Material Ingredient Optimization | Yes
QA-MTS-002 | QA Rebar B | Rev 00 | Under review | All metals | MW-05 | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) Material technical datasheets confirming the recycled content of steel. | Yes |  | %
QA-MTS-002 | QA Rebar B | Rev 00 | Under review | All metals | MW-05 | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 2) Purchase orders for all reinforcing or stressing steel installed in the project. | Yes
QA-MTS-002 | QA Rebar C | Rev 00 | C | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 1) Environmental Product Declaration (EPD): Provide any of the below: a) Manufacturer declared life-cycle assessment with at least a cradle to gate scope. b) Manufacturer reviewed product specific Type III EPD with at least a cradle to gate scope c) Third party verified industry-wide Type III EPD with at least a cradle to gate scope. | Yes
QA-MTS-002 | QA Rebar C | Rev 00 | C | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 2) Embodied Carbon/LCA Optimization: Provide manufactures prepared Embodied Carbon/LCA Action Plan demonstrating reduction in embodied carbon with at least reduction in GWP. | Yes
QA-MTS-002 | QA Rebar C | Rev 00 | C | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) A manufacturer declaration/third party certificate stating the % of post-consumer and % of pre-consumer recycled content. Note: Waste reuse from the same production line should be excluded. 2) If applicable, a manufacturer letter stating the products sourced (extracted, manufactured and purchased) is within 160 km of the project site. | Yes
QA-MTS-002 | QA Rebar C | Rev 00 | C | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 3) Invoices/Purchase orders | Yes
QA-MTS-002 | QA Rebar C | Rev 00 | C | For all materials | RC-01 |  | 1) Proof of manufacture in KSA, with at least one of the following conditions: - Extracted in KSA - Manufactured in KSA - Final point of assembly in KSA | Yes
QA-MTS-002 | QA Rebar C | Rev 00 | C | For all materials | RC-01 |  | 2) Invoices/Purchase orders | Yes
QA-MTS-002 | QA Rebar C | Rev 00 | C | For all materials |  | MRc4: Building Product Disclosure and Optimization - Material Ingredients | Provide any of below documentation: - Cradle to Cradle (C2C): Material Health Certificate or is Cradle to Cradle Certified™ Bronze level or higher. - Declare: Designated as Red List Free, LBC Red List Free, or Declared, LBC Red List Approved or LBC Compliant - Global Green Tag or Health Product Declaration (HPDs). Material Ingredient Optimization: Provide anyone of below: - Manufacturer prepared REACH report or PHD Report verified by Global Green TAG - Manufacturer prepared material ingredient screening and Optimization Action Plan - Third party verified Advanced Inventory & Assessment - Third party verified Material Ingredient Optimization | Yes
QA-MTS-002 | QA Rebar C | Rev 00 | C | All metals | MW-05 | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) Material technical datasheets confirming the recycled content of steel. | Yes |  | %
QA-MTS-002 | QA Rebar C | Rev 00 | C | All metals | MW-05 | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 2) Purchase orders for all reinforcing or stressing steel installed in the project. | Yes
QA-MTS-002 | QA Rebar D | Rev 00 | D | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 1) Environmental Product Declaration (EPD): Provide any of the below: a) Manufacturer declared life-cycle assessment with at least a cradle to gate scope. b) Manufacturer reviewed product specific Type III EPD with at least a cradle to gate scope c) Third party verified industry-wide Type III EPD with at least a cradle to gate scope. | Yes
QA-MTS-002 | QA Rebar D | Rev 00 | D | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 2) Embodied Carbon/LCA Optimization: Provide manufactures prepared Embodied Carbon/LCA Action Plan demonstrating reduction in embodied carbon with at least reduction in GWP. | Yes
QA-MTS-002 | QA Rebar D | Rev 00 | D | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) A manufacturer declaration/third party certificate stating the % of post-consumer and % of pre-consumer recycled content. Note: Waste reuse from the same production line should be excluded. 2) If applicable, a manufacturer letter stating the products sourced (extracted, manufactured and purchased) is within 160 km of the project site. | Yes
QA-MTS-002 | QA Rebar D | Rev 00 | D | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 3) Invoices/Purchase orders | Yes
QA-MTS-002 | QA Rebar D | Rev 00 | D | For all materials | RC-01 |  | 1) Proof of manufacture in KSA, with at least one of the following conditions: - Extracted in KSA - Manufactured in KSA - Final point of assembly in KSA | Yes
QA-MTS-002 | QA Rebar D | Rev 00 | D | For all materials | RC-01 |  | 2) Invoices/Purchase orders | Yes
QA-MTS-002 | QA Rebar D | Rev 00 | D | For all materials |  | MRc4: Building Product Disclosure and Optimization - Material Ingredients | Provide any of below documentation: - Cradle to Cradle (C2C): Material Health Certificate or is Cradle to Cradle Certified™ Bronze level or higher. - Declare: Designated as Red List Free, LBC Red List Free, or Declared, LBC Red List Approved or LBC Compliant - Global Green Tag or Health Product Declaration (HPDs). Material Ingredient Optimization: Provide anyone of below: - Manufacturer prepared REACH report or PHD Report verified by Global Green TAG - Manufacturer prepared material ingredient screening and Optimization Action Plan - Third party verified Advanced Inventory & Assessment - Third party verified Material Ingredient Optimization | Yes
QA-MTS-002 | QA Rebar D | Rev 00 | D | All metals | MW-05 | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) Material technical datasheets confirming the recycled content of steel. | Yes |  | %
QA-MTS-002 | QA Rebar D | Rev 00 | D | All metals | MW-05 | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 2) Purchase orders for all reinforcing or stressing steel installed in the project. | Yes
QA-MTS-001 | QA Exterior paint | Rev 00 | A | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 1) Environmental Product Declaration (EPD): Provide any of the below: a) Manufacturer declared life-cycle assessment with at least a cradle to gate scope. b) Manufacturer reviewed product specific Type III EPD with at least a cradle to gate scope c) Third party verified industry-wide Type III EPD with at least a cradle to gate scope. | Yes
QA-MTS-001 | QA Exterior paint | Rev 00 | A | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 2) Embodied Carbon/LCA Optimization: Provide manufactures prepared Embodied Carbon/LCA Action Plan demonstrating reduction in embodied carbon with at least reduction in GWP. | Yes
QA-MTS-001 | QA Exterior paint | Rev 00 | A | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) A manufacturer declaration/third party certificate stating the % of post-consumer and % of pre-consumer recycled content. Note: Waste reuse from the same production line should be excluded. 2) If applicable, a manufacturer letter stating the products sourced (extracted, manufactured and purchased) is within 160 km of the project site. | Yes
QA-MTS-001 | QA Exterior paint | Rev 00 | A | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 3) Invoices/Purchase orders | Yes
QA-MTS-001 | QA Exterior paint | Rev 00 | A | For all materials | RC-01 |  | 1) Proof of manufacture in KSA, with at least one of the following conditions: - Extracted in KSA - Manufactured in KSA - Final point of assembly in KSA | Yes
QA-MTS-001 | QA Exterior paint | Rev 00 | A | For all materials | RC-01 |  | 2) Invoices/Purchase orders | Yes
QA-MTS-001 | QA Exterior paint | Rev 00 | A | For all materials |  | MRc4: Building Product Disclosure and Optimization - Material Ingredients | Provide any of below documentation: - Cradle to Cradle (C2C): Material Health Certificate or is Cradle to Cradle Certified™ Bronze level or higher. - Declare: Designated as Red List Free, LBC Red List Free, or Declared, LBC Red List Approved or LBC Compliant - Global Green Tag or Health Product Declaration (HPDs). Material Ingredient Optimization: Provide anyone of below: - Manufacturer prepared REACH report or PHD Report verified by Global Green TAG - Manufacturer prepared material ingredient screening and Optimization Action Plan - Third party verified Advanced Inventory & Assessment - Third party verified Material Ingredient Optimization | Yes
QA-MTS-001 | QA Exterior paint | Rev 00 | A | Paints, Coatings (QA) | HC-11 | IEQc2: Low-Emitting Materials | 1) Data sheet or Test Report for Product VOC Content (g/l) complying with the VOC content requirements for wet-applied products AND 2) General emission certificate as per CDPH Standard Method v1,1 or v1.2 2017 with testing lab accreditation under ISO/IEC 17025. | Yes |  | g/L | ≤ 50 g/L (QA) |  | RISE-CDPH-emission-report-O100152.pdf (2026-10-01)
QA-MTS-001 | QA Exterior paint | Rev 00 | A | Paints, Coatings (QA) | HC-11 |  | QA extra row: provide the colour card | Yes
QA-MTS-002 | QA Bike rack | Rev 00 | Under review | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 1) Environmental Product Declaration (EPD): Provide any of the below: a) Manufacturer declared life-cycle assessment with at least a cradle to gate scope. b) Manufacturer reviewed product specific Type III EPD with at least a cradle to gate scope c) Third party verified industry-wide Type III EPD with at least a cradle to gate scope. | N/A
QA-MTS-002 | QA Bike rack | Rev 00 | Under review | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 2) Embodied Carbon/LCA Optimization: Provide manufactures prepared Embodied Carbon/LCA Action Plan demonstrating reduction in embodied carbon with at least reduction in GWP. | N/A
QA-MTS-002 | QA Bike rack | Rev 00 | Under review | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) A manufacturer declaration/third party certificate stating the % of post-consumer and % of pre-consumer recycled content. Note: Waste reuse from the same production line should be excluded. 2) If applicable, a manufacturer letter stating the products sourced (extracted, manufactured and purchased) is within 160 km of the project site. | N/A
QA-MTS-002 | QA Bike rack | Rev 00 | Under review | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 3) Invoices/Purchase orders | N/A
QA-MTS-002 | QA Bike rack | Rev 00 | Under review | For all materials | RC-01 |  | 1) Proof of manufacture in KSA, with at least one of the following conditions: - Extracted in KSA - Manufactured in KSA - Final point of assembly in KSA | N/A
QA-MTS-002 | QA Bike rack | Rev 00 | Under review | For all materials | RC-01 |  | 2) Invoices/Purchase orders | N/A
QA-MTS-002 | QA Bike rack | Rev 00 | Under review | For all materials |  | MRc4: Building Product Disclosure and Optimization - Material Ingredients | Provide any of below documentation: - Cradle to Cradle (C2C): Material Health Certificate or is Cradle to Cradle Certified™ Bronze level or higher. - Declare: Designated as Red List Free, LBC Red List Free, or Declared, LBC Red List Approved or LBC Compliant - Global Green Tag or Health Product Declaration (HPDs). Material Ingredient Optimization: Provide anyone of below: - Manufacturer prepared REACH report or PHD Report verified by Global Green TAG - Manufacturer prepared material ingredient screening and Optimization Action Plan - Third party verified Advanced Inventory & Assessment - Third party verified Material Ingredient Optimization | N/A
QA-MTS-002 | QA Bike rack | Rev 00 | Under review | Bike racks | TC-04 | LTc6: Bicycle Facilities | 1) Data sheet/Manufacturer Information/shop drawings of bicycle racks with locations as per the authority approved design drawings. | N/A
QA-MTS-002 | QA Bike rack | Rev 00 | Under review | Bike racks | TC-04 | LTc6: Bicycle Facilities | 2) Purchase receipts of all shading devices installed in the bicycle parking space. | N/A
QA-MTS-001 | QA Paint A | Rev 02 | Under review | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 1) Environmental Product Declaration (EPD): Provide any of the below: a) Manufacturer declared life-cycle assessment with at least a cradle to gate scope. b) Manufacturer reviewed product specific Type III EPD with at least a cradle to gate scope c) Third party verified industry-wide Type III EPD with at least a cradle to gate scope. | Yes
QA-MTS-001 | QA Paint A | Rev 02 | Under review | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 2) Embodied Carbon/LCA Optimization: Provide manufactures prepared Embodied Carbon/LCA Action Plan demonstrating reduction in embodied carbon with at least reduction in GWP. | Yes
QA-MTS-001 | QA Paint A | Rev 02 | Under review | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) A manufacturer declaration/third party certificate stating the % of post-consumer and % of pre-consumer recycled content. Note: Waste reuse from the same production line should be excluded. 2) If applicable, a manufacturer letter stating the products sourced (extracted, manufactured and purchased) is within 160 km of the project site. | Yes
QA-MTS-001 | QA Paint A | Rev 02 | Under review | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 3) Invoices/Purchase orders | Yes
QA-MTS-001 | QA Paint A | Rev 02 | Under review | For all materials | RC-01 |  | 1) Proof of manufacture in KSA, with at least one of the following conditions: - Extracted in KSA - Manufactured in KSA - Final point of assembly in KSA | Yes
QA-MTS-001 | QA Paint A | Rev 02 | Under review | For all materials | RC-01 |  | 2) Invoices/Purchase orders | Yes
QA-MTS-001 | QA Paint A | Rev 02 | Under review | For all materials |  | MRc4: Building Product Disclosure and Optimization - Material Ingredients | Provide any of below documentation: - Cradle to Cradle (C2C): Material Health Certificate or is Cradle to Cradle Certified™ Bronze level or higher. - Declare: Designated as Red List Free, LBC Red List Free, or Declared, LBC Red List Approved or LBC Compliant - Global Green Tag or Health Product Declaration (HPDs). Material Ingredient Optimization: Provide anyone of below: - Manufacturer prepared REACH report or PHD Report verified by Global Green TAG - Manufacturer prepared material ingredient screening and Optimization Action Plan - Third party verified Advanced Inventory & Assessment - Third party verified Material Ingredient Optimization | Yes
QA-MTS-001 | QA Paint A | Rev 02 | Under review | Paints, Coatings (QA) | HC-11 | IEQc2: Low-Emitting Materials | 1) Data sheet or Test Report for Product VOC Content (g/l) complying with the VOC content requirements for wet-applied products AND 2) General emission certificate as per CDPH Standard Method v1,1 or v1.2 2017 with testing lab accreditation under ISO/IEC 17025. | Yes | 35 | g/L | ≤ 50 g/L (QA) | QA remark | Jotun-VOC-content-test-2022.pdf (2023-05-01) RISE-CDPH-emission-report-O100152.pdf (2026-08-01)
QA-MTS-001 | QA Paint A | Rev 02 | Under review | Paints, Coatings (QA) | HC-11 |  | QA extra row: provide the colour card | Yes
QA-MTS-001 | QA Paint A | Rev 02 | Under review | QA Waterproofing membranes |  |  | QA membrane datasheet | Yes

## Credits
Credit | Part | Basis | Target (%) | Forecast (%) | Actual (%) | Pending (%) | Products counting | Products in scope
MW-05 | Recycled steel | weight | 50 | 57.1 | 100 | 42.9 | 1 | 3
MW-05 | Recycled aggregates | volume | 15 |  |  |  | 0 | 0
MW-05 | Certified timber | cost | 50 |  |  |  | 0 | 0
HC-11 | Low-VOC adhesives, sealants, paints and coatings | weight | 95 | 0 | 0 | 0 | 0 | 1
HC-11 | Formaldehyde: composite wood and ceilings | count | 100 |  |  |  | 0 | 0
RC-01 | Materials made in KSA | cost | 20 / 40 | 18 | 5 | 0 | 3 | 6
MW-04 | Non-polluting insulation | count | 100 |  |  |  | 0 | 0