## Tracker
Project: Jeddah Central Oceanarium
Rating system: Mostadam commercial D+C (2019)
Sustainability Material Tracker · generated 2026-10-27 · credit columns as at 2026-10
[12 empty] | Product |  |  | Quantities | [5 empty] | Counts toward (latest revision) | [6 empty] | SMQ answers by credit |  |  | Review
S/N | Material Submittal Reference | Rev | Approval Status | Description | Date of Submission | Sustainability Applicable | Discipline | Supplier Name | Material Delivery date | Material Delivery (PO Number) | Manufacturer Name | Country of Origin | Location of use | Interior | BOQ weight (t) | BOQ volume (m³) | BOQ cost (SAR) | Delivered weight (t) | Delivered volume (m³) | Delivered cost (SAR) | MW-05 Recycled steel | MW-05 Recycled aggregates | MW-05 Certified timber | HC-11 Low-VOC adhesives, sealants, paints and coatings | HC-11 Formaldehyde: composite wood and ceilings | RC-01 Materials made in KSA | MW-04 Non-polluting insulation | HC-11 answers | MW-05 answers | RC-01 answers | Reviewed on | Reviewed by | Consultant remarks
1 | JCD-OCN-MBL-PRO-MTS-0411-00 | Rev 00 | C - Revise and resubmit | All epoxy flooring systems: Jotafloor Easyflow Primer HS | 2026-04-28 |  | Architecture | Jotun Saudi Limited |  |  | Jotun Saudi Limited | Norway | Flooring | Yes | [9 empty] | Pending |  | Pending |  | Yes 45 g/L |  | No; - | 2026-05-05 | Waqas Tariq | Provided documents: 1. EPD 2. VOC emissions test report & content test reports. VOC content is expired; an updated test report shall be provided.
2 | JCD-OCN-MBL-PRO-TBE-0001-00 | Rev 00 | A - Approved | Technical bid evaluation for epoxy coated steel rebars: Epoxy coated rebar — ITTIFAQ | 2026-03-15 |  | Civil |  | 2026-06-30 2026-07-14 | 2403879 2409874 | ITTIFAQ | Saudi Arabia |  | Yes | 600 |  | 1920000 | 550 |  | 1760000 | Counts |  |  |  |  | Counts |  |  | Yes 85 %; Yes | Yes; Yes | 2026-05-05 | Waqas Tariq
3 | JCD-OCN-MBL-PRO-TBE-0001-00 | Rev 00 | B - Approved as noted | Technical bid evaluation for epoxy coated steel rebars: Epoxy coated rebar — WESTERN STEEL | 2026-03-15 |  | Civil |  | 2026-07-02 | 2404660 | WESTERN STEEL | Saudi Arabia |  | Yes | 300 |  | 960000 | 120 |  | 384000 | Counts |  |  |  |  | Counts |  |  | Yes 85 %; Yes | Yes; Yes | 2026-06-10 | Waqas Tariq
4 | JCD-OCN-MBL-PRO-TBE-0001-00 | Rev 00 | C - Revise and resubmit | Technical bid evaluation for epoxy coated steel rebars: Epoxy coated rebar — THILAL | 2026-03-15 |  | Civil |  |  |  | THILAL | Saudi Arabia |  | Yes | 100 |  | 320000 |  |  |  | Pending |  |  |  |  | Pending |  |  | Yes 85 %; Yes | Yes; Yes | 2026-07-20 | Waqas Tariq

## Answers
Submittal | Product | Rev | Status | Section | Mostadam credit | LEED reference | Required documents / parameters | Answer | Value | Unit | Project target | Remark | Documents (issue date)
JCD-OCN-MBL-PRO-MTS-0411-00 | Jotafloor Easyflow Primer HS | Rev 00 | C | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 1) Environmental Product Declaration (EPD): Provide any of the below: a) Manufacturer declared life-cycle assessment with at least a cradle to gate scope. b) Manufacturer reviewed product specific Type III EPD with at least a cradle to gate scope c) Third party verified industry-wide Type III EPD with at least a cradle to gate scope. | Yes
JCD-OCN-MBL-PRO-MTS-0411-00 | Jotafloor Easyflow Primer HS | Rev 00 | C | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 2) Embodied Carbon/LCA Optimization: Provide manufactures prepared Embodied Carbon/LCA Action Plan demonstrating reduction in embodied carbon with at least reduction in GWP.
JCD-OCN-MBL-PRO-MTS-0411-00 | Jotafloor Easyflow Primer HS | Rev 00 | C | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) A manufacturer declaration/third party certificate stating the % of post-consumer and % of pre-consumer recycled content. Note: Waste reuse from the same production line should be excluded. 2) If applicable, a manufacturer letter stating the products sourced (extracted, manufactured and purchased) is within 160 km of the project site.
JCD-OCN-MBL-PRO-MTS-0411-00 | Jotafloor Easyflow Primer HS | Rev 00 | C | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 3) Invoices/Purchase orders
JCD-OCN-MBL-PRO-MTS-0411-00 | Jotafloor Easyflow Primer HS | Rev 00 | C | For all materials | RC-01 |  | 1) Proof of manufacture in KSA, with at least one of the following conditions: - Extracted in KSA - Manufactured in KSA - Final point of assembly in KSA | No |  |  |  | Proof on KSA manufacturing was not found - to be provided in the next stage.
JCD-OCN-MBL-PRO-MTS-0411-00 | Jotafloor Easyflow Primer HS | Rev 00 | C | For all materials | RC-01 |  | 2) Invoices/Purchase orders
JCD-OCN-MBL-PRO-MTS-0411-00 | Jotafloor Easyflow Primer HS | Rev 00 | C | For all materials |  | MRc4: Building Product Disclosure and Optimization - Material Ingredients | Provide any of below documentation: - Cradle to Cradle (C2C): Material Health Certificate or is Cradle to Cradle Certified™ Bronze level or higher. - Declare: Designated as Red List Free, LBC Red List Free, or Declared, LBC Red List Approved or LBC Compliant - Global Green Tag or Health Product Declaration (HPDs). Material Ingredient Optimization: Provide anyone of below: - Manufacturer prepared REACH report or PHD Report verified by Global Green TAG - Manufacturer prepared material ingredient screening and Optimization Action Plan - Third party verified Advanced Inventory & Assessment - Third party verified Material Ingredient Optimization
JCD-OCN-MBL-PRO-MTS-0411-00 | Jotafloor Easyflow Primer HS | Rev 00 | C | Paints & Coatings | HC-11 | IEQc2: Low-Emitting Materials | 1) Data sheet or Test Report for Product VOC Content (g/l) complying with the VOC content requirements for wet-applied products AND 2) General emission certificate as per CDPH Standard Method v1,1 or v1.2 2017 with testing lab accreditation under ISO/IEC 17025. | Yes | 45 | g/L |  |  | Jotun-VOC-content-test-2022.pdf (2022-03-01) RISE-CDPH-emission-report-O100152.pdf (2023-05-12)
JCD-OCN-MBL-PRO-MTS-0411-00 | Jotafloor Easyflow Primer HS | Rev 00 | C | Carpet, Hard Flooring |  | IEQc2: Low-Emitting Materials | General emission certificate as per CDPH Standard Method v1.1 or v1.2 with testing lab accreditation under ISO/IEC 17025.
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — ITTIFAQ | Rev 00 | A | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 1) Environmental Product Declaration (EPD): Provide any of the below: a) Manufacturer declared life-cycle assessment with at least a cradle to gate scope. b) Manufacturer reviewed product specific Type III EPD with at least a cradle to gate scope c) Third party verified industry-wide Type III EPD with at least a cradle to gate scope.
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — ITTIFAQ | Rev 00 | A | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 2) Embodied Carbon/LCA Optimization: Provide manufactures prepared Embodied Carbon/LCA Action Plan demonstrating reduction in embodied carbon with at least reduction in GWP.
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — ITTIFAQ | Rev 00 | A | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) A manufacturer declaration/third party certificate stating the % of post-consumer and % of pre-consumer recycled content. Note: Waste reuse from the same production line should be excluded. 2) If applicable, a manufacturer letter stating the products sourced (extracted, manufactured and purchased) is within 160 km of the project site.
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — ITTIFAQ | Rev 00 | A | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 3) Invoices/Purchase orders
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — ITTIFAQ | Rev 00 | A | For all materials | RC-01 |  | 1) Proof of manufacture in KSA, with at least one of the following conditions: - Extracted in KSA - Manufactured in KSA - Final point of assembly in KSA | Yes
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — ITTIFAQ | Rev 00 | A | For all materials | RC-01 |  | 2) Invoices/Purchase orders | Yes
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — ITTIFAQ | Rev 00 | A | For all materials |  | MRc4: Building Product Disclosure and Optimization - Material Ingredients | Provide any of below documentation: - Cradle to Cradle (C2C): Material Health Certificate or is Cradle to Cradle Certified™ Bronze level or higher. - Declare: Designated as Red List Free, LBC Red List Free, or Declared, LBC Red List Approved or LBC Compliant - Global Green Tag or Health Product Declaration (HPDs). Material Ingredient Optimization: Provide anyone of below: - Manufacturer prepared REACH report or PHD Report verified by Global Green TAG - Manufacturer prepared material ingredient screening and Optimization Action Plan - Third party verified Advanced Inventory & Assessment - Third party verified Material Ingredient Optimization
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — ITTIFAQ | Rev 00 | A | All metals | MW-05 | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) Material technical datasheets confirming the recycled content of steel. | Yes | 85 | % |  |  | Datasheet-Jotafloor-Easyflow-Primer-HS.pdf (2025-11-02)
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — ITTIFAQ | Rev 00 | A | All metals | MW-05 | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 2) Purchase orders for all reinforcing or stressing steel installed in the project. | Yes
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — WESTERN STEEL | Rev 00 | B | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 1) Environmental Product Declaration (EPD): Provide any of the below: a) Manufacturer declared life-cycle assessment with at least a cradle to gate scope. b) Manufacturer reviewed product specific Type III EPD with at least a cradle to gate scope c) Third party verified industry-wide Type III EPD with at least a cradle to gate scope.
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — WESTERN STEEL | Rev 00 | B | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 2) Embodied Carbon/LCA Optimization: Provide manufactures prepared Embodied Carbon/LCA Action Plan demonstrating reduction in embodied carbon with at least reduction in GWP.
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — WESTERN STEEL | Rev 00 | B | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) A manufacturer declaration/third party certificate stating the % of post-consumer and % of pre-consumer recycled content. Note: Waste reuse from the same production line should be excluded. 2) If applicable, a manufacturer letter stating the products sourced (extracted, manufactured and purchased) is within 160 km of the project site.
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — WESTERN STEEL | Rev 00 | B | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 3) Invoices/Purchase orders
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — WESTERN STEEL | Rev 00 | B | For all materials | RC-01 |  | 1) Proof of manufacture in KSA, with at least one of the following conditions: - Extracted in KSA - Manufactured in KSA - Final point of assembly in KSA | Yes
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — WESTERN STEEL | Rev 00 | B | For all materials | RC-01 |  | 2) Invoices/Purchase orders | Yes
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — WESTERN STEEL | Rev 00 | B | For all materials |  | MRc4: Building Product Disclosure and Optimization - Material Ingredients | Provide any of below documentation: - Cradle to Cradle (C2C): Material Health Certificate or is Cradle to Cradle Certified™ Bronze level or higher. - Declare: Designated as Red List Free, LBC Red List Free, or Declared, LBC Red List Approved or LBC Compliant - Global Green Tag or Health Product Declaration (HPDs). Material Ingredient Optimization: Provide anyone of below: - Manufacturer prepared REACH report or PHD Report verified by Global Green TAG - Manufacturer prepared material ingredient screening and Optimization Action Plan - Third party verified Advanced Inventory & Assessment - Third party verified Material Ingredient Optimization
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — WESTERN STEEL | Rev 00 | B | All metals | MW-05 | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) Material technical datasheets confirming the recycled content of steel. | Yes | 85 | % |  |  | Datasheet-Jotafloor-Easyflow-Primer-HS.pdf (2025-11-02)
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — WESTERN STEEL | Rev 00 | B | All metals | MW-05 | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 2) Purchase orders for all reinforcing or stressing steel installed in the project. | Yes
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — THILAL | Rev 00 | C | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 1) Environmental Product Declaration (EPD): Provide any of the below: a) Manufacturer declared life-cycle assessment with at least a cradle to gate scope. b) Manufacturer reviewed product specific Type III EPD with at least a cradle to gate scope c) Third party verified industry-wide Type III EPD with at least a cradle to gate scope.
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — THILAL | Rev 00 | C | For all materials |  | MRc2: Building Product Disclosure and Optimization - Environmental Product Declarations | 2) Embodied Carbon/LCA Optimization: Provide manufactures prepared Embodied Carbon/LCA Action Plan demonstrating reduction in embodied carbon with at least reduction in GWP.
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — THILAL | Rev 00 | C | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) A manufacturer declaration/third party certificate stating the % of post-consumer and % of pre-consumer recycled content. Note: Waste reuse from the same production line should be excluded. 2) If applicable, a manufacturer letter stating the products sourced (extracted, manufactured and purchased) is within 160 km of the project site.
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — THILAL | Rev 00 | C | For all materials |  | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 3) Invoices/Purchase orders
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — THILAL | Rev 00 | C | For all materials | RC-01 |  | 1) Proof of manufacture in KSA, with at least one of the following conditions: - Extracted in KSA - Manufactured in KSA - Final point of assembly in KSA | Yes
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — THILAL | Rev 00 | C | For all materials | RC-01 |  | 2) Invoices/Purchase orders | Yes
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — THILAL | Rev 00 | C | For all materials |  | MRc4: Building Product Disclosure and Optimization - Material Ingredients | Provide any of below documentation: - Cradle to Cradle (C2C): Material Health Certificate or is Cradle to Cradle Certified™ Bronze level or higher. - Declare: Designated as Red List Free, LBC Red List Free, or Declared, LBC Red List Approved or LBC Compliant - Global Green Tag or Health Product Declaration (HPDs). Material Ingredient Optimization: Provide anyone of below: - Manufacturer prepared REACH report or PHD Report verified by Global Green TAG - Manufacturer prepared material ingredient screening and Optimization Action Plan - Third party verified Advanced Inventory & Assessment - Third party verified Material Ingredient Optimization
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — THILAL | Rev 00 | C | All metals | MW-05 | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 1) Material technical datasheets confirming the recycled content of steel. | Yes | 85 | % |  |  | Datasheet-Jotafloor-Easyflow-Primer-HS.pdf (2025-11-02)
JCD-OCN-MBL-PRO-TBE-0001-00 | Epoxy coated rebar — THILAL | Rev 00 | C | All metals | MW-05 | MRc3:Building Product Disclosure and Optimization - Sourcing of Raw Materials | 2) Purchase orders for all reinforcing or stressing steel installed in the project. | Yes

## Credits
Credit | Part | Basis | Target (%) | Forecast (%) | Actual (%) | Pending (%) | Products counting | Products in scope
MW-05 | Recycled steel | weight | 50 | 90 | 100 | 10 | 2 | 3
MW-05 | Recycled aggregates | volume | 15 |  |  |  | 0 | 0
MW-05 | Certified timber | cost | 50 |  |  |  | 0 | 0
HC-11 | Low-VOC adhesives, sealants, paints and coatings | weight | 95 |  |  |  | 0 | 1
HC-11 | Formaldehyde: composite wood and ceilings | count | 100 |  |  |  | 0 | 0
RC-01 | Materials made in KSA | cost | 20 / 40 | 90 | 100 | 10 | 2 | 4
MW-04 | Non-polluting insulation | count | 100 |  |  |  | 0 | 0